## Attendance
Employee ID | Employee Name | Date | In Time | Out Time | Shift Hours | Site
E101 | Raj | 2026-06-01 | 09:00 | 20:00 | 8 | Powai DSS
E118 | Sunil | 2026-06-05 | 09:00 | 23:00 | 8 | Market City
E122 | Amit | 2026-06-06 | 08:30 | 19:30 | 8 | Glen Height CSS

## Overtime Claims
Employee ID | Employee Name | Date | OT Claimed Hours | Work Description | Reason
E101 | Raj | 2026-06-01 | 2 | Transformer maintenance and oil leakage inspection | Bushing cleaning and safety checks extended work
E118 | Sunil | 2026-06-05 | 6 | Cable fault repair and termination | Additional cable damage found during restoration
E122 | Amit | 2026-06-06 | 3 | Feeder restoration after trip | Emergency outage restoration

## Crew Deployment
Date | Crew Lead | Crew Members | Department | Site | Assigned Work
2026-06-01 | Raj | Raj, Mohan | Distribution | Powai DSS | Transformer maintenance
2026-06-05 | Sunil | Sunil, Karan | Cable | Market City | Cable fault repair
2026-06-06 | Amit | Amit, Dev | Distribution Control | Glen Height CSS | Feeder restoration

## Completion Reports
Date | Site | Work Completed | Additional Work Found | Testing/Proof
2026-06-01 | Powai DSS | Transformer maintenance completed | Damaged cable lugs tightened and bushing cleaned | Oil leakage checked; load normalized
2026-06-05 | Market City | Cable fault localized and repaired | Cable termination replaced | Megger test passed; feeder restored
2026-06-06 | Glen Height CSS | Feeder restored after trip | Load transfer and patrolling required | SCADA event matched outage

## Work Benchmarks
Work Type | Expected Duration Hours | Electrical Segment
Fuse Replacement | 0.75 | Distribution
Meter Replacement | 0.5 | Metering
Transformer Maintenance | 2.5 | Distribution/Substation
Cable Fault Repair | 4 | Underground Distribution
Feeder Restoration | 2 | Distribution Control
Relay Protection Testing | 4 | Protection and Control